## Overview
Short form description (scroll down for expanded description)
Overview
The following Excel spreadsheet is a project management tool that takes a proposed pre-trial schedule and then breaks down the individual tasks needed to meet that schedule. We are then able to track the activities of those working on the project while also unearthing details that allow for more accurate budgeting of the project, as well as tracking against an existing budget.
Litigation model | Project Management tool kit
- Models the tasks typically required to prepare for an upcoming trial
- Assumptions are (1) a legal staff of eight at our disposal (2) 15 witnesses for direct examination, of which three are expert witnesses and, (3) 18 adversarial witnesses for cross examination, of which 10 are expert witnesses. | Budget and Work Plan
- Additionally, evidence will need to be catalogued, and various graphics need to be created.
Schedule
- Provides a timeline for the expected completion dates of necessary tasks
- This forces consideration of both the amount of time individual tasks require, and the sequence in which the tasks logically should be performed to prepare efficiently for trial.
Teams
- Assigns legal staff to necessary tasks
- Each staff member is assigned to a team with one or more other legal staff
o At this stage, redundancy of expertise and case knowledge is critical.
- Did not try to balance the workload between the various staff, instead based the assignments on capability, expertise, and case knowledge acquired to date
- Allows an overview of “what is staff member X doing”
Workplan & Assignments
- Two sheets which are mirror images of each other
- The Workplan breaks down the assigned task by topic and allows us to see who is responsible for completing a particular task, and other details.
- The “Assignments” focuses on the legal staff and date involved, rather than the task itself.
Budget
- The top of the Budget sheet shows the hourly billing rate for each legal staff member, and from this creates a blended rate for the team they are on
- Using a simple “hours x rates” calculation we are able to estimate the fee for completing a particular task
- We can then total these fees to provide an estimate of the entire project
- Presenting the individual hours estimates by timekeeper makes the buildup of the budget transparent to all stakeholders
Long form description
Overview
The following Excel spreadsheet is a project management tool that takes a proposed pre-trial schedule and then breaks down the individual tasks needed to meet that schedule. We are then able to track the activities of those working on the project while also unearthing details that allow for more accurate budgeting of the project, as well as tracking against an existing budget.
Litigation Model
The model project is a large, complex and high stakes litigation. We have modeled the tasks typically required to prepare for an upcoming trial, and assumed we had a legal staff of eight at our disposal. We further assumed that there would be:
- 15 witnesses for direct examination, of which 3 are expert witnesses
- 18 adversarial witnesses for cross examination, of which 10 are expert witnesses
In addition, we assumed that evidence would need to be catalogued, and that various graphics would need to be created.
Upon opening the file, we see five tabs at the bottom of the window. Each tab displays different worksheets, which in compilation provide various views and predictions of the project plan.
Schedule
The first worksheet is labeled “Schedule,” and shows the tasks requiring completion. The target timeline provides the expected completion dates for the various tasks. Creating this timeline forces consideration of both the amount of time individual tasks require, and the sequence in which the tasks logically should be performed to prepare efficiently for trial. After completing the schedule, we are able to begin assigning the tasks to various legal staff.
Teams
The “Teams” page takes the schedule of tasks and assigns them to various legal staff. Because the model project is a large and complex litigation, everything is done in conjunction with other staff. At this stage redundancy of expertise and case knowledge is critical, and ensures that the litigation is not adversely affected if one team member goes down unexpectedly. Therefore, each staff member is assigned to a team with other legal staff. For example, if Partner A is the project manager, Associate A and Associate B are each teamed with Partner A, who will be overseeing their work. Similarly, Counsel A and Counsel C are teamed together, and we assume they require less supervision than the associates, as well has having certain subject matter expertise which leads to their being assigned much of the cross examination of expert witnesses.
Notably, we did not make much effort in balancing the workload between the various staff. Instead we based the assignments on capability and acquired case expertise to date, so as to maximize return on case investments up to this point.
The Teams sheet allows an overview of “what is staff member X doing” and, in conjunction with the Schedule sheet, allows us to make the “Workplan” and “Assignments” sheets.
Workplan & Assignments
The Workplan breaks down the assigned task by topic, and allows us to see who is responsible for completing a particular task, as well as providing some details on the type of deliverable, format, and manner of preparation.
The “Assignments” sheet is a mirror image of the Workplan, and focuses on the legal staff and date involved, rather than the task itself.
Combined, these two sheets take the information from the Schedule and Teams pages, and turns it into an easily referenced format.
Budget
The top of the Budget sheet shows the hourly billing rate for each legal staff member, and from this creates a blended rate for the team they are on. For example, the Alpha Team is comprised of Partner A and Associate A, and assumes that for every four hours worked on a task by associate A, one hour from Partner A will be required for supervision. Accordingly, the blended rate is based on 80% of Associate A’s hourly rate, and 20% of Partner A’s rate.
Using these rates we then list all of the necessary tasks, and estimate the amount of time required for completion by the assigned team. Using a simple “hours x rates” calculation we are able to estimate the fees for completing a particular task. Then, using the tabulation functions in the software, we can total these fees to provide an estimate of the entire project. By presenting the individual hours estimates by timekeeper, the buildup of the budget is transparent to all stakeholders

## Schedule
PRE-TRIAL SCHEDULE PHASE II (TARGET TIMELINE) |  | PRE-TRIAL SCHEDULE PHASE III (DEADLINES IMPOSED BY COURT)
Week 1 |  | 2010-06-01 | Parties exchange exhibit lists, exhibits, witness lists, and deposition designations
Deposition designations -- finalized
Exhibits -- initial compilation
|  | 2010-06-05 | Parties exchange objections to exhibits and deposition counter-designations
Week 2
Direct examinations finalized for: Witnesses 1, 2, 3
| Graphics -- initial drafts created | 2010-06-12 | Parties file joint pre-trial order
Week 3 |  | 2010-06-19 | Parties file motions in limine
Direct examinations finalized for: Witness 4-8
| Exhibit List -- initial draft | 2010-06-25 | Parties file oppositions to motions in limine
Witness List -- initial draft
Week 4
| Direct examinations finalized for: Witnesses 9-12 | 2010-07-09 | Trial begins
Direct examinations finalized for: Experts 1-3
Week 5
Cross-examinations finalized for: Expert Adverse-1 and Expert Adverse-2
Cross-examinations finalized for: Witness Adverse 1 through 5
Week 6
Cross-examinations finalized for: Expert Adverse 3 - 7
Exhibit list -- finalized
Witness list -- finalized
Week 7
Cross-examinations finalized for: Expert Adverse 8 - 10
Exhibits -- compilation finalized
Graphics -- finalized
Week 8
Cross-examinations finalized for: Witness Adverse 6 - 8
Week 9 | PRE-TRIAL SCHEDULE PHASE III (DEADLINES IMPOSED BY COURT)

## Workplan
STEP NO. | TIMELINE | ACTIVITY | RESPONSIBILITY |  | DELIVERABLES | FORMAT | PREPARATION
Direct Exams
| Week 2 | Finalize Direct of W1, W2, W3 | Alpha Team | Partner A; Associate A | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 3 | Finalize Direct of W4, W5 | Alpha Team | Partner A; Associate A | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 3 | Finalize Direct of W6, W7, W8 | Beta Team | Partner A; Associate B | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 4 | Finalize direct examinations W9, W10, W11, W12 | Gamma Team | Partner B; Associate A | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 4 | Finalize direct exam of Ex1 and Ex2 | Beta Team | Partner A; Associate B | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 4 | Finalize direct exam of Ex3 | Delta Team | Counsel A; Counsel C | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
Cross Exams
| Week 5 | Finalize Cross Exams for ExAd-1 and ExAd-2 | Beta Team | Partner A; Associate B | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 5 | Finalize cross-examinations W-Ad1, W-Ad2, W-Ad3 | Alpha Team | Partner A; Associate A | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 5 | Finalize cross-examinations W-Ad4, W-Ad5 | Gamma Team | Partner B; Associate A | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 6 | Finalize cross exam for: ExAd-3, ExAd-4, ExAd-5, ExAd-6, ExAd-7 | Delta Team | Counsel A; Counsel C | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 7 | Finalize cross-examinations for ExAd-8, ExAd-9, ExAd-10 | Delta Team | Counsel A; Counsel C | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
| Week 8 | Finalize cross-exam of W-Ad6, W-Ad7, W-Ad8 | Alpha Team | Partner A; Associate A | Written questions | Written notes, section of trial notebook | Review existing deposition, prepare questions in consultation with trial themes team
Graphics and Exhibits
| Week 1 | Exhibits -- initial compilation | Graph and Exhib team | Counsel B; Paralegal P | 1st draft of exhibit compilation | Written lists and graphics | Prepare list
| Week 2 | Initial drafts of graphics | Graph and Exhib team | Counsel B; Paralegal P | 1st draft of graphics | Written description and sketches | Describe graphics, call Print Co. for printing options
| Week 3 | Exhibit List -- initial draft | Graph and Exhib team | Counsel B; Paralegal P | Exhibit list | Written list | Discuss with Partner A and other teams to determine which exhibits will be needed at trial
| Week 6 | Exhibit list -- finalized | Graph and Exhib team | Counsel B; Paralegal P | Exhibit list | Written list | Discuss with Partner A and other teams to determine which exhibits will be needed at trial
Lists and Other Prep
| Week 1 | Finalize deposition designations for Alpha Group witnesses | Alpha Team | Partner A; Associate A | Deposition designations to show to opposing counsel. | Written Document | Review existing depositions in consultation with trial themes team
| Week 1 | Finalize deposition designations for Beta Group witnesses | Beta Team | Partner A; Associate B | Deposition designations to show to opposing counsel. | Written Document | Review existing depositions in consultation with trial themes team
| Week 1 | Finalize deposition designations for Gamma Group witnesses | Gamma Team | Partner B; Associate A | Deposition designations to show to opposing counsel. | Written Document | Review existing depositions in consultation with trial themes team
| Week 1 | Finalize deposition designations for Delta Group witnesses | Delta Team | Counsel A; Counsel C | Deposition designations to show to opposing counsel. | Written Document | Review existing depositions in consultation with trial themes team
| Week 3 | Witness List -- initial draft | Lists team | Counsel B; Paralegal P | Written List of Witnesses | Written List | Discuss with Partner A and other teams to determine which witnesses will be needed at trial
| Week 6 | Witness list -- finalized | Lists team | Counsel B; Paralegal P | Written List of Witnesses | Written List | Discuss with Partner A and other teams to determine which witnesses will be needed at trial

## Teams
PROPOSED PRE-TRIAL TEAMS & TASKS
Available Staff
Partner A
Partner B
Counsel A
Counsel B
Counsel C
Associate A
Associate B
Paralegal P
Teams | Members | Witness Group | Direct | Cross
Alpha | Partner A; Associate A | Witness Group Alpha | W1, W2, W3, W4, W5 | W-Ad1, W-Ad2, W-Ad3. W-Ad6, W-Ad7, W-Ad8
Beta | Partner A; Associate B | Witness Group Beta | W6, W7, W8, Ex1, Ex2 | Ex-Ad1, Ex-Ad2,
Gamma | Partner B; Associate A | Witness Group Gamma | W9, W10, W11, W12 | W-Ad4, W-Ad5
Delta | Counsel A; Counsel C | Witness Group Delta | Ex3 | ExAd-3, ExAd-4, ExAd-5, ExAd-6, ExAd-7, ExAd-8, ExAd-9, ExAd-10
Graphics & Exhibits | Counsel B; Paralegal P
Pre-trial lists | Partner B; Paralegal P
Trial themes | Partners A & B; Counsel C; Associate A
DIRECT EXAMINATION SCRIPTS
Witness Name | Abbreviation | Assigned Team | Staff
Expert 1 | Ex1 | Beta | Partner A; Associate B
Expert 2 | Ex2 | Beta | Partner A; Associate B
Expert 3 | Ex3 | Delta | Counsel A; Counsel C
Witness 1 | W1 | Alpha | Partner A; Associate A
Witness 2 | W2 | Alpha | Partner A; Associate A
Witness 3 | W3 | Alpha | Partner A; Associate A
Witness 4 | W4 | Alpha | Partner A; Associate A
Witness 5 | W5 | Alpha | Partner A; Associate A
Witness 6 | W6 | Beta | Partner A; Associate B
Witness 7 | W7 | Beta | Partner A; Associate B
Witness 8 | W8 | Beta | Partner A; Associate B
Witness 9 | W9 | Gamma | Partner B; Associate A
Witness 10 | W10 | Gamma | Partner B; Associate A
Witness 11 | W11 | Gamma | Partner B; Associate A
Witness 12 | W12 | Gamma | Partner B; Associate A
CROSS-EXAMINATION SCRIPTS (Adverse Witnesses)
Witness Name | Abbreviation | Team | Staff
Expert Adversary-1 | ExAd-1 | Beta | Partner A; Associate B
Expert Adversary-2 | ExAd-2 | Beta | Partner A; Associate B
Expert Adversary-3 | ExAd-3 | Delta | Counsel A; Counsel C
Expert Adversary-4 | ExAd-4 | Delta | Counsel A; Counsel C
Expert Adversary-5 | ExAd-5 | Delta | Counsel A; Counsel C
Expert Adversary-6 | ExAd-6 | Delta | Counsel A; Counsel C
Expert Adversary-7 | ExAd-7 | Delta | Counsel A; Counsel C
Expert Adversary-8 | ExAd-8 | Delta | Counsel A; Counsel C
Expert Adversary-9 | ExAd-9 | Delta | Counsel A; Counsel C
Expert Adversary-10 | ExAd-10 | Delta | Counsel A; Counsel C
Witness Adversary-1 | W-Ad1 | Alpha | Partner A; Associate A
Witness Adversary-2 | W-Ad2 | Alpha | Partner A; Associate A
Witness Adversary-3 | W-Ad3 | Alpha | Partner A; Associate A
Witness Adversary-4 | W-Ad4 | Gamma | Partner B; Associate A
Witness Adversary-5 | W-Ad5 | Gamma | Partner B; Associate A
Witness Adversary-6 | W-Ad6 | Alpha | Partner A; Associate A
Witness Adversary-7 | W-Ad7 | Alpha | Partner A; Associate A
Witness Adversary-8 | W-Ad8 | Alpha | Partner A; Associate A

## Assignments
PRE-TRIAL ASSIGNMENTS PHASE II
Team Member | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Team Member | Week 7 | Week 8 | Week 9
Partner A | Deposition Designations due for assigned witnesses | Finalize Direct of W1, W2, W3 | Finalize Direct of W4, W5, W6, W7, W8 | Finalize Direct of Ex1, Ex2 | Cross-examinations finalized for: Ex-A1 and Ex-A2, W-A1, W-A2, W-A3 |  | Partner A |  | Cross-examinations finalized for: Witnesses A6-A8 | Beginning of Phase III - Court Imposed Deadlines
Partner B | Deposition Designations due for assigned witnesses, pre-trial lists |  | Draft Exhibit List and Witness List | Direct examinations finalized for W9, W10, W11, W12 | Cross-exam finalized for W-A4, W-A5 | Finalize Exhibit List and Witness List | Partner B
Counsel A | Deposition Designations due for assigned witnesses |  |  | Direct Exam Finalized for Ex3 |  | Cross-examinations finalized for: ExAds 3-7 | Counsel A | Cross-examinations finalized for: ExAds 8-10
Counsel B | Initial Composition of exhibits | Initial drafts of graphics |  |  |  |  | Counsel B | Finalize Graphics and Exhibits
Counsel C | Deposition Designations due for assigned witnesses |  |  | Direct Exam Finalized for Ex3 |  | Cross-examinations finalized for: ExAds 3-7 | Counsel C | Cross-examinations finalized for: ExAds 8-10
Associate A | Deposition Designations due for assigned witnesses | Finalize Direct of W1, W2, W3 | Finalize Direct of W4, W5 | Direct examinations finalized for W9, W10, W11, W12 | Cross-examinations finalized for W-Ad1, W-Ad2, W-Ad3, W-Ad4, W-Ad5 |  | Associate A |  | Cross-examinations finalized for: W-Ad 6 through 8
Associate B | Deposition Designations due for assigned witnesses |  | Finalize Direct of W6, W7, W8 | Finalize Direct of Ex1, Ex2 | Cross-examinations finalized for: ExAd-1 and ExAd-2 |  | Associate B
Paralegal P | Initial Composition of exhibits and pre-trial lists | Initial drafts of graphics | Draft Exhibit List and Witness List |  |  | Finalize Exhibit List and Witness List | Paralegal P | Finalize Graphics and Exhibits

## Budget
TRIAL PREP (MATTER TYPE) - PROPOSED BUDGET - FEE/COST ANALYSIS ASSUMPTIONS
KEY: | Blue = | Input/assumption
| Inputs: | Hourly Rates for: | Hourly Rate (US$) | Total Est Hours | Total Est Fees (US$)
|  | Partner A | 750 | 14.55 | 10912.5
|  | Partner B | 600 | 4.15 | 2490
|  | Counsel A | 400 | 14.5 | 5800
|  | Counsel B | 425 | 3 | 1275
|  | Counsel C | 425 | 14.5 | 6162.5
|  | Associate A | 340 | 35.2 | 11968
|  | Associate B | 360 | 16.25 | 5850
|  | Paralegal P | 150 | 14.85 | 2227.5
|  | Total Cost of Phase II |  | 117 | 46685.5
Staffing Ratios |  | Based on Team Assignments:
should reflect |  | Alpha Team (20% Partner A, 80% Associate A) | 422 | 29 | 12238
risk and complexity (1) |  | Beta Team (35% Partner A, 65% Associate B) | 496.5 | 25 | 12412.5
(from client perspective) |  | Gamma Team (25% Partner B, 75% Associate A) | 405 | 16 | 6480
skills, expertise |  | Delta Team (50% Counsel A, 50% Counsel C) | 412.5 | 29 | 11962.5
resource alternatives (2) |  | Graphics & Exhibits (20% Counsel B, 80% Paralegal P) | 205 | 15 | 3075
(from law firm perspective) |  | Pre-trial lists (Partner B 5%, Paralegal P 95%) | 172.5 | 3 | 517.5
|  | Total Cost of Phase II |  | 117 | 46685.5
(1) Based on
- scope of work
- definition of success
(2) Based on leverage, profitability, optimizing workflows to fully utilize team members
PRE-TRIAL PHASE II COSTS
Preparation and Planning
STEP NO. | TIMELINE | ACTIVITY | TEAM | HOURS | FEES (US$)
Direct Exam Scripts
| Week 2 | Witness 1 | Alpha | 3 | 1266
| Week 2 | Witness 2 | Alpha | 4 | 1688
| Week 2 | Witness 3 | Alpha | 2 | 844
| Week 3 | Witness 4 | Alpha | 3 | 1266
| Week 3 | Witness 5 | Alpha | 2 | 844
| Week 3 | Witness 6 | Beta | 2 | 993
| Week 3 | Witness 7 | Beta | 1 | 496.5
| Week 3 | Witness 8 | Beta | 5 | 2482.5
| Week 4 | Witness 9 | Gamma | 3 | 1215
| Week 4 | Witness 10 | Gamma | 3 | 1215
| Week 4 | Witness 11 | Gamma | 1 | 405
| Week 4 | Witness 12 | Gamma | 2 | 810
| Week 4 | Expert 1 | Beta | 5 | 2482.5
| Week 4 | Expert 2 | Beta | 2 | 993
| Week 4 | Expert 3 | Delta | 3 | 1237.5
|  | Total Cost of Direct Exam Scripts |  | 41 | 18238
|  | Average cost of direct exam script | 1215.8667
STEP NO. | TIMELINE | ACTIVITY | TEAM | HOURS | COST
Cross Exam Scripts
| Week 5 | Expert Adversary 1 | Beta | 2 | 993
| Week 5 | Expert Adversary 2 | Beta | 6 | 2979
| Week 5 | Witness Adversary 1 | Alpha | 2 | 844
| Week 5 | Witness Adversary 2 | Alpha | 4 | 1688
| Week 5 | Witness Adversary 3 | Alpha | 3 | 1266
| Week 5 | Witness Adversary 4 | Gamma | 2 | 810
| Week 5 | Witness Adversary 5 | Gamma | 3 | 1215
| Week 6 | Expert Adversary 3 | Delta | 4 | 1650
| Week 6 | Expert Adversary 4 | Delta | 1 | 412.5
| Week 6 | Expert Adversary 5 | Delta | 2 | 825
| Week 6 | Expert Adversary 6 | Delta | 2 | 825
| Week 6 | Expert Adversary 7 | Delta | 2 | 825
| Week 7 | Expert Adversary 8 | Delta | 4 | 1650
| Week 7 | Expert Adversary 9 | Delta | 6 | 2475
| Week 7 | Expert Adversary 10 | Delta | 3 | 1237.5
| Week 8 | Witness Adversary 6 | Alpha | 2 | 844
| Week 8 | Witness Adversary 7 | Alpha | 1 | 422
| Week 8 | Witness Adversary 8 | Alpha | 1 | 422
|  | Total Cost of Cross Exam Scripts |  | 50 | 21383
|  | Average cost of cross exam script | 1187.9444
STEP NO. | TIMELINE | ACTIVITY | TEAM | HOURS | FEES
Graphics and Exhibits
| Week 1 | Exhibits -- initial compilation | Grph&Ex | 3 | 615
| Week 2 | Initial drafts of graphics | Grph&Ex | 6 | 1230
| Week 3 | Exhibit List -- initial draft | Grph&Ex | 2 | 410
| Week 6 | Exhibit list -- finalized | Grph&Ex | 4 | 820
|  | Total Cost of Graphs and Exhibits |  | 15 | 3075
STEP NO. | TIMELINE | ACTIVITY | TEAM | HOURS | FEES
Lists and Other Prep
| Week 1 | Finalize deposition designations for Alpha Group witnesses | Alpha | 2 | 844
| Week 1 | Finalize deposition designations for Beta Group witnesses | Beta | 2 | 993
| Week 1 | Finalize deposition designations for Gamma Group witnesses | Gamma | 2 | 810
| Week 1 | Finalize deposition designations for Delta Group witnesses | Delta | 2 | 825
| Week 3 | Witness List -- initial draft | Lists | 1.5 | 258.75
| Week 6 | Witness list -- finalized | Lists | 1.5 | 258.75
|  | Total Cost of Graphs and Exhibits |  | 11 | 3989.5
TOTAL FEES |  |  |  | 117 | 46685.5
|  | Average Blended hourly rate | 399.0214
Costs Per Week
| Week 1 |  | 4087
| Week 2 |  | 5028
| Week 3 |  | 6750.75
| Week 4 |  | 8358
| Week 5 |  | 9795
| Week 6 |  | 5616.25
| Week 7 |  | 5362.5
| Week 8 |  | 1688
| Total |  | 46685.5