## Project Team
Stakeholders Matrix
[SYSTEM] Implementation Project Management |  |  | Date Updated: MM/DD/YYYY
PROJECT CHARTER: Project Goal: The project goal is the implementation of a [SYSTEM] at [COMPANY] to support its strategic goals. Project Objectives: 1. … 2. … 3. …
Steering Committee |  | Core Working Team
Subject Matter Experts
[SUB-WORKSTREAM] | [SUB-WORKSTREAM] | [SUB-WORKSTREAM] | [SUB-WORKSTREAM]
[SUB-WORKSTREAM] | [SUB-WORKSTREAM] | [SUB-WORKSTREAM] | [SUB-WORKSTREAM]
Note on A5: A Project Goal is the outcome of the discrete project (i.e., the successful implementation of the system). A Project Objective is the desired impact of the Project Goal (e.g., utilizing data from the system to inform business decisions).
Note on A7: The Steering Committee is responsible for providing final signoff and resolving any escalated issues. It should include: 1. Executive Sponsor 2. Key Stakeholder/Subject Matter Expert from focus Practice Areas, Regions, etc. 3. Lead Project Managers from IT, the selected Vendor, and any consultant partners. The Steering Committee should meet regularly to review project status, resolve open dependencies and risks, and make project decisions.
Note on C7: The Core Working Team is responsible for day-to-day project execution. It should include: 1. All Project Managers (from Legal, IT, the Vendor, any consultant partners, etc.) 2. All Developers and Testers currently working on the project 3. Representatives from other areas of the organization, as necessary (e.g., Finance, Supply Chain/Procurement) Depending on the implementation methodology (e.g., Waterfall, Agile), the Core Working Team could meet daily or weekly.
Note on A14: Depending on the type of system being implemented, and the complexity of the organization, design requirements may need to be collected from Subject Matter Experts. For example: Subject Matter Experts may provide insight into: 1. Law Department Practice Area 2. Region, Subregion or Country 3. Product Line 4. Subsidiary or associated organization 5. Internal support function

## Tasks
|  | Task Description | Owner | Start Date | End Date | Dependencies | Notes
1.00 Project Management
| 1.01 | Prepare project kickoff materials
| 1.02 | Schedule project kickoff meeting
| 1.03 | Conduct project kickoff meeting
| 1.04 | Prepare weekly status reports |  |  |  |  | Recurring meeting; frequency to be determined by team
| 1.05 | Conduct weekly status meeting |  |  |  |  | Recurring meeting; frequency to be determined by team
| 1.06 | Prepare monthly Steering Committee reports |  |  |  |  | Recurring meeting; frequency to be determined by team
| 1.07 | Conduct monthly Steering Committee meeting |  |  |  |  | Recurring meeting; frequency to be determined by team
2.00 Environment Setup
| 2.01 | Sandbox | Vendor
| 2.02 | QA (Pre-Staging) | Vendor
| 2.03 | UAT/Performance Testing (Staging 1) | Vendor |  |  |  | UAT/Performance Testing and Training environments may be the same
| 2.04 | Training (Staging 2) | Vendor |  |  |  | UAT/Performance Testing and Training environments may be the same
| 2.05 | Production | Vendor
3.00 Requirements Gathering & Design
| 3.01 | Review Department taxonomy materials |  |  |  |  | If Department already has a taxonomy, this can be leveraged. Otherwise, a new taxonomy may need to be developed.
| 3.02 | Prepare requirements gathering and design workshop materials |  |  |  |  | To the extent that requirements and design can be anticipated, workshops should be used to validate requirements.
| 3.03 | Schedule Practice Area sessions
| 3.04 | Conduct Practice Area 1 session |  |  |  |  | Practice Area can be substituted with Region, Product Line, Support Function etc.
| 3.05 | Conduct Practice Area 2 session |  |  |  |  | Practice Area can be substituted with Region, Product Line, Support Function etc.
| 3.06 | Conduct Practice Area 3 session |  |  |  |  | Practice Area can be substituted with Region, Product Line, Support Function etc.
| 3.07 | Conduct Practice Area 4 session |  |  |  |  | Practice Area can be substituted with Region, Product Line, Support Function etc.
| 3.08 | Conduct Practice Area 5 session |  |  |  |  | Practice Area can be substituted with Region, Product Line, Support Function etc.
| 3.09 | Document requirements gathered in sessions
| 3.1 | Schedule Steering Committee sign-off meeting
| 3.11 | Obtain Steering Committee sign-off on requirements
| 3.12 | Draft design document
| 3.13 | Obtain Vendor feedback on design document |  |  |  |  | Depending on the agreement with the Vendor, this step may include an estimate of development costs
| 3.14 | Schedule Steering Committee sign-off meeting
| 3.15 | Obtain Steering Committee sign-off on design
4.00 Development
| 4.01 | Set up required servers and environments | Vendor
| 4.02 | Develop configurations of application | Vendor
| 4.03 | Develop integration points | Vendor
| 4.04 | Unit test development environment | Vendor
5.00 Testing
| 5.01 | Prepare test cases | Vendor
| 5.02 | End to end testing of configuration (in QA environment) | Vendor
| 5.03 | End to end testing of integration (in QA environment) | Vendor |  |  |  | Only necessary if the system is integrated with other systems
| 5.04 | End to end testing of data migration (in QA environment) | Vendor |  |  |  | Only necessary if data has been migrated to the system
| 5.05 | Resolve and re-test defects (from QA testing)
| 5.06 | Complete UAT plan (participants, schedule and resources)
| 5.07 | Develop UAT scripts, including desired outcomes
| 5.08 | Develop UAT training materials
| 5.09 | Schedule UAT
| 5.1 | Conduct UAT Training |  |  |  |  | UAT Training can be conducted in advance of or concurrently with UAT
| 5.11 | Conduct UAT with selected end-users
| 5.12 | Resolve and re-test defects (from UAT)
| 5.13 | Schedule Steering Committee sign-off meeting
| 5.14 | Obtain Steering Committee sign-off on UAT
6.00 Training
| 6.01 | Draft Training Plan
| 6.02 | Schedule Steering Committee sign-off meeting
| 6.03 | Obtain Steering Committee sign-off on Training Plan
| 6.04 | Draft Training Materials
| 6.05 | Schedule Steering Committee sign-off meeting
| 6.06 | Obtain Steering Committee sign-off on Training Materials
| 6.07 | Schedule Training sessions
| 6.08 | Conduct Administrator training |  |  |  |  | Administrator (or Train-the-Trainer) Training is for those that will be responsible for administering the system (e.g., access rights, dropdown values)
| 6.09 | Conduct end-user training
7.00 Cutover & Rollout
| 7.01 | Set up user accounts
| 7.02 | Schedule Go/No-Go decision meeting with Steering Committee
| 7.03 | Obtain Go/No-Go decision
| 7.04 | Conduct final data conversion
| 7.05 | Announce System Go-Live
| 7.06 | Go-Live
| 7.07 | Monitor initial use and address issues found